## List
TASK OR TITLE
MAKE A LIST |  |  | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
START DATE | TASK | END DATE
2024-11-18 | Client Meeting | 2024-11-18 | bar: 19
2024-11-19 | Outline Fucntions | 2024-11-19 | bar: 20
2024-11-20 | Create a Gantt Chart | 2024-11-22 | bar: 21 to 22
2024-11-23 | Writing Psuedocode | 2024-11-23 | bar: 24
2024-11-24 | Implementing core functionality | 2024-11-24 | bar: 25
2024-11-25 | Ensure that the code adheres to good programming practices. | 2024-11-25 | bar: 26
2024-11-26 | Client Meeting, present wok to Ms Kakar | 2024-11-27 | bar: 26 to 27
2024-11-27 | Implement features based on client specifications | 2024-11-28 | bar: 28 to 29
2024-11-29 | Provide a comprehensive test plan | 2024-11-29 | bar: 30
2024-11-30 | Document security concerns and describe steps address them. | 2024-11-30 | bar: 1
2024-12-01 | Inlcude comments, a user manual and a developer guide | 2024-12-01 | bar: 2
2024-12-02 | Present the final program to Ms.Kakar and explain the approach. | 2024-12-02 | bar: 3
2024-12-03 | Submit a final reflection on the development process and the lessons learned in te process | 2024-12-05 | bar: 4 to 6